## ProjectStatusReport(May)-GovD
CRM Team- Accessibility Compliance - (03/19/2026 through 04/15/2026)
Project Health |  |  | Project Information (Sprint 1157 & 1158)
Trend | Status | Indicators | Project Name | Improve Granicus govDelivery Capabilities
↑ | IN PROGRESS | Overall | Project Request ID | 202511042
↑ | IN PROGRESS | Milestones | Project Sponsor | Chris Bucher
↔ | IN PROGRESS | Stakeholder Engagement | Project Manager | Vindhya Rao Jajavarapu
↑ | ON TRACK | Scope | Program Area | Division of Government & Public Affairs / Office of Communication
↑ | ON TRACK | Budget | Products Impacted | CRM Marketting Module
↑ | ON TRACK | Timeline | Project Objectives | Migrate CRM newsletters to GovDelivery, retire the CRM marketing module, and enable automated, role-based contact communication.
Status help |  |  | Value Proposition | Cuts costs and manual work while making communication more accurate and targeted.
Dropdown here for Status Description |  |  | School and District Impact | N/A
Status help screen |  |  | Project Phases & Timeline
|  |  |  | Target Start Date | Target End Date | Actual Start Date | Actual End Date | Status
|  |  | Planning Phase | Dec, 20 | Jan, 25 | Dec, 20 | Jan, 25 | COMPLETE
|  |  | Construction Phase | Jan, 5 | Apr, 24 | Jan, 5 | Apr, 24 | IN PROGRESS
|  |  | Close Out Phase | Apr, 27 | Apr, 29 | Apr, 27 | Apr, 29 | IN PROGRESS
Critical Milestones
|  |  |  | Target Start Date | Target End Date | Actual Start Date | Actual End Date | Status
|  |  | Milestone 1: Project Planning and Business Approval for Project | Dec, 20 | Jan, 25 | Jan, 25 | Mar, 25 | Completed
|  |  | Milestone 2: Working with Architects for Initial project/application and pipeline set up | Dec, 20 | Apr,25 | Apr,25 | Apr,25 | In Progress
|  |  | Milestone 3: Walkthrough the proposed solution with IT leadership and architects | Dec, 20 / prior dates | Apr,25 | Dec, 20 / prior dates | Mar, 25 | In Progress
|  |  | Milestone 4 Active Development | Jan, 5 | Mar,5 |  |  | In Progress
|  |  | Milestone 5:UAT Feedback/Enhancements | Jan,25 | Apr, 25 |  |  | In Progress
|  |  | Milestone 6: Close out | Apr, 27 | Apr, 29
Issues and Risks
|  |  | No | Risk / issue Description |  |  | Response Status | Impact
Change Requests
|  |  | No | Change Description |  |  | Requestor | Impact
Next Month Activities (Sprint 1156)
Work Item No
|  |  | USERSTORY243331 | Melissa Eggert- Provision CRM Access for New Partner Support Team Member | Melissa Eggert- Provision CRM Access for New Partner Support Team Member | Melissa Eggert- Provision CRM Access for New Partner Support Team Member | Melissa Eggert- Provision CRM Access for New Partner Support Team Member | Melissa Eggert- Provision CRM Access for New Partner Support Team Member
|  |  | USERSTORY243171 | SM - School Modification Form Grade Levels | SM - School Modification Form Grade Levels | SM - School Modification Form Grade Levels | SM - School Modification Form Grade Levels | SM - School Modification Form Grade Levels
|  |  | USERSTORY243086 | Ensure cases assigned to 'Michelle Silverman' and and 'DawnMerth-Johnson' appear in SPED-Ed Active Cases queue | Ensure cases assigned to 'Michelle Silverman' and and 'DawnMerth-Johnson' appear in SPED-Ed Active Cases queue | Ensure cases assigned to 'Michelle Silverman' and and 'DawnMerth-Johnson' appear in SPED-Ed Active Cases queue | Ensure cases assigned to 'Michelle Silverman' and and 'DawnMerth-Johnson' appear in SPED-Ed Active Cases queue | Ensure cases assigned to 'Michelle Silverman' and and 'DawnMerth-Johnson' appear in SPED-Ed Active Cases queue
|  |  | USERSTORY242845 | SM - Adding the validation for the name fields | SM - Adding the validation for the name fields | SM - Adding the validation for the name fields | SM - Adding the validation for the name fields | SM - Adding the validation for the name fields
|  |  | USERSTORY242837 | Accessibility Fixes - Formatting for portal pages after Accessibility requirements updates | Accessibility Fixes - Formatting for portal pages after Accessibility requirements updates | Accessibility Fixes - Formatting for portal pages after Accessibility requirements updates | Accessibility Fixes - Formatting for portal pages after Accessibility requirements updates | Accessibility Fixes - Formatting for portal pages after Accessibility requirements updates
|  |  | USERSTORY242835 | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors
|  |  | USERSTORY242841 | LEAD : Clean up LEAD KB portal | LEAD : Clean up LEAD KB portal | LEAD : Clean up LEAD KB portal | LEAD : Clean up LEAD KB portal | LEAD : Clean up LEAD KB portal
|  |  | USERSTORY243074 | Accessibility Fixes : Knowledge articles CST | Accessibility Fixes : Knowledge articles CST | Accessibility Fixes : Knowledge articles CST | Accessibility Fixes : Knowledge articles CST | Accessibility Fixes : Knowledge articles CST
|  |  | USERSTORY242844 | Use Service accounts to authenticate with Sharepoint for PA flows | Use Service accounts to authenticate with Sharepoint for PA flows | Use Service accounts to authenticate with Sharepoint for PA flows | Use Service accounts to authenticate with Sharepoint for PA flows | Use Service accounts to authenticate with Sharepoint for PA flows
|  |  | USERSTORY242846 | CRM: Clean up Logs to free up some space | CRM: Clean up Logs to free up some space | CRM: Clean up Logs to free up some space | CRM: Clean up Logs to free up some space | CRM: Clean up Logs to free up some space
|  |  | USERSTORY242836 | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes
|  |  | USERSTORY242840 | QA - LEAD KB Articles validation after the accessibility WCAG 2.1 changes | QA - LEAD KB Articles validation after the accessibility WCAG 2.1 changes | QA - LEAD KB Articles validation after the accessibility WCAG 2.1 changes | QA - LEAD KB Articles validation after the accessibility WCAG 2.1 changes | QA - LEAD KB Articles validation after the accessibility WCAG 2.1 changes
Last Month Activities (Sprint 1157 & 1158) - Project Tickets
Work Item No
Sprint 1155
|  |  | USERSTORY241907 | Accessibility Fixes - Lead contact pages (Screen Reader) | Accessibility Fixes - Lead contact pages (Screen Reader) | Accessibility Fixes - Lead contact pages (Screen Reader) | Accessibility Fixes - Lead contact pages (Screen Reader) | Accessibility Fixes - Lead contact pages (Screen Reader)
|  |  | USERSTORY241906 | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors - Cont. | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors - Cont. | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors - Cont. | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors - Cont. | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors - Cont.
|  |  | USERSTORY241908 | Test and Validate Rollback Plan for Accessibility Releases - Power Pages | Test and Validate Rollback Plan for Accessibility Releases - Power Pages | Test and Validate Rollback Plan for Accessibility Releases - Power Pages | Test and Validate Rollback Plan for Accessibility Releases - Power Pages | Test and Validate Rollback Plan for Accessibility Releases - Power Pages
|  |  | USERSTORY242325 | Accessibilty Headers and errors resolve on remaining KB
Sprint 1156
|  |  | USERSTORY242837 | Accessibility Fixes - Formatting for portal pages after Accessibility requirements updates | Accessibility Fixes - Formatting for portal pages after Accessibility requirements updates | Accessibility Fixes - Formatting for portal pages after Accessibility requirements updates | Accessibility Fixes - Formatting for portal pages after Accessibility requirements updates | Accessibility Fixes - Formatting for portal pages after Accessibility requirements updates
|  |  | USERSTORY242835 | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors
|  |  | USERSTORY243074 | Accessibility Fixes : Knowledge articles CST | Accessibility Fixes : Knowledge articles CST | Accessibility Fixes : Knowledge articles CST | Accessibility Fixes : Knowledge articles CST | Accessibility Fixes : Knowledge articles CST
|  |  | USERSTORY242836 | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes
Non - Project related activities ( Project Drag- 1157 & 1158)
|  |  | Tasks / Stories / Bugs |  | Requestor |  | Priortization reason
Sprint 1154 Sprint 1153
|  |  | USERSTORY240307 |  | Kurra Venkatesh |  | Microsoft Ticket_ KB Articles Issue
|  |  | USERSTORY240260 |  | Cynthia Hoffman |  | Verify on Subscribe Pages in GovD
|  |  | USERSTORY240259 |  | Anderson Paul |  | LEAD : Alert email failing with old email address
|  |  | USERSTORY239398 |  | Venkatesh Kurra |  | Azure app secret keys expiring by March 3rd
Sprint 1155 Sprint 1154
|  |  | USERSTORY242446 |  | Venkatesh Kurra |  | SM: Full version field is becoming read only, update USPS API, add alert notifications
|  |  | USERSTORY242245 |  | Rupesh Makula |  | Fix error when uploading documents in School Modification Form - Emergency Ticket
|  |  | USERSTORY241901 |  | Rupesh Makula |  | LEAD- Sync licenses , applications for contacts
|  |  | USERSTORY241736 |  | Rupesh Makula |  | LEAD_ Licensing - Remove the ability to delete contacts from the TEPDL team member role
|  |  | USERSTORY242322 |  | Rupesh Makula |  | Fix error when uploading documents in School Modification Form - Emergency Ticket
|  |  | USERSTORY242231 |  | Venkatesh Kurra |  | Validate All SharePoint Libraries Use Modern Authentication
|  |  | USERSTORY240529 |  | Rupesh Makula |  | LEAD : Inactive users assigned cases
[6 empty] | Dropdown here for Status Description | Status help screen
|  |  | Critical | Accepted - No action | ↑ | ON TRACK | Tasks are worked upon and the team is working towards the target date and is on time to meet the schedule
|  |  | High | Transferred | ↓ | IN PROGRESS | Tasks are worked upon and the team is working towards the target date but does not have estimated time of completion and cannot forecast any issues in the project
|  |  | Medium | Avoided | ↔ | OVERDUE | Task that is past their given timeline to complete
|  |  | Low | Mitigated |  | COMPLETE | Work on the project has finished, and all deliverables/tasks have been completed
[6 empty] | ON HOLD | The project has not finished, and work on the project has been temporarily suspended
[6 empty] | CANCELLED | The project has not finished, and work on the project will not continue
[6 empty] | NOT STARTED | Efforts that are not started
Dropdown here for Status Description
ON TRACK
| IN PROGRESS | In Progress
| OVERDUE | Not Started
| COMPLETE | Completed
ON HOLD
CANCELLED
NOT STARTED
Note on H2023: Anand, Chamu DPI: IN PROGRESS : Tasks are worked upon and the team is working towards the target date but does not have estimated time of completion and cannot forecast any issues in the project.
Note on B2038: Anand, Chamu DPI: IN PROGRESS : Tasks are worked upon and the team is working towards the target date but does not have estimated time of completion and cannot forecast any issues in the project.

## ProjectStatusReport(May)-AccSca
CRM Team- Accessibility Compliance - (03/19/2026 through 04/15/2026)
Project Health |  |  | Project Information (Sprint 1157 & 1158)
Trend | Status | Indicators | Project Name | Accessibility Compliance
↑ | IN PROGRESS | Overall | Project Request ID | 202511042
↑ | IN PROGRESS | Milestones | Project Sponsor | Lucas Munz
↔ | IN PROGRESS | Stakeholder Engagement | Project Manager | Vindhya Rao Jajavarapu
↑ | ON TRACK | Scope | Program Area | Bureau of Information Technology Services
↑ | ON TRACK | Budget | Products Impacted | All CRM Priority One public facing applications
↑ | ON TRACK | Timeline | Project Objectives | Conduct security scans on Applications so that potential vulnerabilities can be identified and remediated.
Status help |  |  | Value Proposition | Strengthen accessibility compliance and deliver an inclusive user experience across applications.
Dropdown here for Status Description |  |  | School and District Impact | N/A
Status help screen |  |  | Project Phases & Timeline
|  |  |  | Target Start Date | Target End Date | Actual Start Date | Actual End Date | Status
|  |  | Planning Phase | Dec, 20 | Jan, 25 | Dec, 20 | Jan, 25 | COMPLETE
|  |  | Construction Phase | Jan, 5 | Apr, 24 | Jan, 5 | Apr, 24 | COMPLETE
|  |  | Close Out Phase | Apr, 27 | Apr, 29 | Apr, 27 | Apr, 29 | COMPLETE
Critical Milestones
|  |  |  | Target Start Date | Target End Date | Actual Start Date | Actual End Date | Status
|  |  | Milestone 1: Project Planning and Business Approval for Project | Dec, 20 | Jan, 25 | Jan, 25 | Mar, 25 | Completed
|  |  | Milestone 2: Working with Architects for Initial project/application and pipeline set up | Dec, 20 | Apr,25 | Apr,25 | Apr,25 | Completed
|  |  | Milestone 3: Walkthrough the proposed solution with IT leadership and architects | Dec, 20 / prior dates | Apr,25 | Dec, 20 / prior dates | Mar, 25 | Completed
|  |  | Milestone 4 Active Development | Jan, 5 | Mar,5 | Jan, 5 | Apr, 25 | Completed
|  |  | Milestone 5:UAT Feedback/Enhancements | Jan,25 | Apr, 25 | Jan,25 | Apr, 25 | Completed
|  |  | Milestone 6: Close out | Apr, 27 | Apr, 29 | Apr, 27 | May, 12 | Completed
Issues and Risks
|  |  | No | Risk / issue Description |  |  | Response Status | Impact
Change Requests
|  |  | No | Change Description |  |  | Requestor | Impact
Next Month Activities (Sprint 1159)
Work Item No
|  |  | USERSTORY243331 | Melissa Eggert- Provision CRM Access for New Partner Support Team Member | Melissa Eggert- Provision CRM Access for New Partner Support Team Member | Melissa Eggert- Provision CRM Access for New Partner Support Team Member | Melissa Eggert- Provision CRM Access for New Partner Support Team Member | Melissa Eggert- Provision CRM Access for New Partner Support Team Member
|  |  | USERSTORY243171 | SM - School Modification Form Grade Levels | SM - School Modification Form Grade Levels | SM - School Modification Form Grade Levels | SM - School Modification Form Grade Levels | SM - School Modification Form Grade Levels
|  |  | USERSTORY243086 | Ensure cases assigned to 'Michelle Silverman' and and 'DawnMerth-Johnson' appear in SPED-Ed Active Cases queue | Ensure cases assigned to 'Michelle Silverman' and and 'DawnMerth-Johnson' appear in SPED-Ed Active Cases queue | Ensure cases assigned to 'Michelle Silverman' and and 'DawnMerth-Johnson' appear in SPED-Ed Active Cases queue | Ensure cases assigned to 'Michelle Silverman' and and 'DawnMerth-Johnson' appear in SPED-Ed Active Cases queue | Ensure cases assigned to 'Michelle Silverman' and and 'DawnMerth-Johnson' appear in SPED-Ed Active Cases queue
|  |  | USERSTORY242845 | SM - Adding the validation for the name fields | SM - Adding the validation for the name fields | SM - Adding the validation for the name fields | SM - Adding the validation for the name fields | SM - Adding the validation for the name fields
|  |  | USERSTORY242837 | Accessibility Fixes - Formatting for portal pages after Accessibility requirements updates | Accessibility Fixes - Formatting for portal pages after Accessibility requirements updates | Accessibility Fixes - Formatting for portal pages after Accessibility requirements updates | Accessibility Fixes - Formatting for portal pages after Accessibility requirements updates | Accessibility Fixes - Formatting for portal pages after Accessibility requirements updates
|  |  | USERSTORY242835 | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors | Accessibility Fixes: GED HSED - GED HSED Screen reader is not reading out the validation errors
|  |  | USERSTORY242841 | LEAD : Clean up LEAD KB portal | LEAD : Clean up LEAD KB portal | LEAD : Clean up LEAD KB portal | LEAD : Clean up LEAD KB portal | LEAD : Clean up LEAD KB portal
|  |  | USERSTORY243074 | Accessibility Fixes : Knowledge articles CST | Accessibility Fixes : Knowledge articles CST | Accessibility Fixes : Knowledge articles CST | Accessibility Fixes : Knowledge articles CST | Accessibility Fixes : Knowledge articles CST
|  |  | USERSTORY242844 | Use Service accounts to authenticate with Sharepoint for PA flows | Use Service accounts to authenticate with Sharepoint for PA flows | Use Service accounts to authenticate with Sharepoint for PA flows | Use Service accounts to authenticate with Sharepoint for PA flows | Use Service accounts to authenticate with Sharepoint for PA flows
|  |  | USERSTORY242846 | CRM: Clean up Logs to free up some space | CRM: Clean up Logs to free up some space | CRM: Clean up Logs to free up some space | CRM: Clean up Logs to free up some space | CRM: Clean up Logs to free up some space
|  |  | USERSTORY242836 | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes
|  |  | USERSTORY242840 | QA - LEAD KB Articles validation after the accessibility WCAG 2.1 changes | QA - LEAD KB Articles validation after the accessibility WCAG 2.1 changes | QA - LEAD KB Articles validation after the accessibility WCAG 2.1 changes | QA - LEAD KB Articles validation after the accessibility WCAG 2.1 changes | QA - LEAD KB Articles validation after the accessibility WCAG 2.1 changes
Last Month Activities (Sprint 1157 & 1158) - Project Tickets
Work Item No
Sprint 1157
|  |  | USERSTORY243499 | Accessibility Scans KBA Articles - Scans
|  |  | USERSTORY243489 | Accessibility GED/HSED: Add Aria Described by for Radio button fields
|  |  | USERSTORY243493 | Accessibility Fixes : Knowledge articles CST
|  |  | USERSTORY243498 | Accessibility Scans _ KBA Articles - QA
|  |  | USERSTORY242836 | QA - Accessibility Fixes - KB Articles validation after the accessibility WCAG 2.1 changes
Sprint 1158
Non - Project related activities ( Project Drag- 1157 & 1158)
|  |  | Tasks / Stories / Bugs |  | Requestor |  | Priortization reason
Sprint 1157
|  |  | USERSTORY243948 |  | Rupesh Makula |  | SM - Change to School Mod Approvers
|  |  | USERSTORY243876 |  | Kurra Venkatesh |  | PST - Missing Active Cases View for Sean Donohoo
|  |  | USERSTORY243851 |  | Kurra Venkatesh |  | SM - Duplicate Form names on the CRM form
|  |  | USERSTORY243488 |  | Kurra Venkatesh |  | LEAD: Widget is not loading on first open
Sprint 1158
|  |  | USERSTORY242446 |  | Venkatesh Kurra |  | SM: Full version field is becoming read only, update USPS API, add alert notifications
|  |  | USERSTORY242245 |  | Rupesh Makula |  | Fix error when uploading documents in School Modification Form - Emergency Ticket
|  |  | USERSTORY241901 |  | Rupesh Makula |  | LEAD- Sync licenses , applications for contacts
|  |  | USERSTORY241736 |  | Rupesh Makula |  | LEAD_ Licensing - Remove the ability to delete contacts from the TEPDL team member role
|  |  | USERSTORY242322 |  | Rupesh Makula |  | Fix error when uploading documents in School Modification Form - Emergency Ticket
|  |  | USERSTORY242231 |  | Venkatesh Kurra |  | Validate All SharePoint Libraries Use Modern Authentication
|  |  | USERSTORY240529 |  | Rupesh Makula |  | LEAD : Inactive users assigned cases
[6 empty] | Dropdown here for Status Description | Status help screen
|  |  | Critical | Accepted - No action | ↑ | ON TRACK | Tasks are worked upon and the team is working towards the target date and is on time to meet the schedule
|  |  | High | Transferred | ↓ | IN PROGRESS | Tasks are worked upon and the team is working towards the target date but does not have estimated time of completion and cannot forecast any issues in the project
|  |  | Medium | Avoided | ↔ | OVERDUE | Task that is past their given timeline to complete
|  |  | Low | Mitigated |  | COMPLETE | Work on the project has finished, and all deliverables/tasks have been completed
[6 empty] | ON HOLD | The project has not finished, and work on the project has been temporarily suspended
[6 empty] | CANCELLED | The project has not finished, and work on the project will not continue
[6 empty] | NOT STARTED | Efforts that are not started
Dropdown here for Status Description
ON TRACK
| IN PROGRESS | In Progress
| OVERDUE | Not Started
| COMPLETE | Completed
ON HOLD
CANCELLED
NOT STARTED
Note on H2022: Anand, Chamu DPI: IN PROGRESS : Tasks are worked upon and the team is working towards the target date but does not have estimated time of completion and cannot forecast any issues in the project.
Note on B2037: Anand, Chamu DPI: IN PROGRESS : Tasks are worked upon and the team is working towards the target date but does not have estimated time of completion and cannot forecast any issues in the project.

## ENH and Bug Fixes - AccScans
Effort | Category | Value proposition (Sprint 1157 & 1158) | WorkitemID | Workitem Title | Status | Notes
Automatic replies will not create a new case in CRM | Support | Fixes KB article issues to ensure users can access accurate and helpful information without confusion | USERSTORY240307 | Microsoft Ticket_ KB Articles Issue | Completed
Team member app deployment - Ribbon clean up | Support | Ensures subscription pages work correctly, improving user sign-ups and reducing errors. | USERSTORY240260 | Verify on Subscribe Pages in GovD | Completed
Team member app - Adding the resolve button on the ribbon | Bug | Fixes email alert issues so notifications are sent to the correct, updated addresses. | USERSTORY240259 | LEAD : Alert email failing with old email address | Completed
Team member app - Adding the assign button on the ribbon | Enhancement | Prevents service disruptions by renewing expiring keys and maintaining secure system access. | USERSTORY239398 | Azure app secret keys expiring by March 3rd | Completed
Added more info | Bug | Prevent application failures by aligning school year data between systems | USERSTORY242446 | SM: Full version field is becoming read only, update USPS API, add alert notifications | Completed
Time stamp was not showing correctly for specific sped users | Bug | Resolves upload failures so users can submit documents without delays | USERSTORY242245 | Fix error when uploading documents in School Modification Form - Emergency Ticket | Completed
IT related work | Support | Ensures accurate syncing of licenses and applications for better access management. | USERSTORY241901 | LEAD- Sync licenses , applications for contacts | Completed
| Enhancement | Prevents accidental deletion of contacts, improving data security and control. | USERSTORY241736 | LEAD_ Licensing - Remove the ability to delete contacts from the TEPDL team member role | Completed
| Bug | Ensures consistent and reliable document uploads for users. | USERSTORY242322 | Fix error when uploading documents in School Modification Form - Emergency Ticket | Completed
| Support | Strengthens security by enforcing modern authentication across all libraries. | USERSTORY242231 | Validate All SharePoint Libraries Use Modern Authentication | Completed
| Bug | Ensure cases are reassigned from inactive users to active owners to prevent delays and maintain uninterrupted case management. | USERSTORY240529 | LEAD : Inactive users assigned cases | Completed

## Sheet3
1158 - Non Proj
244685 | PST - PS CRM Queue - multiple cases from Christ Lutheran School
244429 | Lead - Update to licensing Contact form
244161 | School Mod Approver Dashboard Enhancement
244091 | VRM Case Notification – Remove Incorrect Recipient
244918 | PR 862 Common Services: Add a button and dialog to configure sync Common Services to GovD - Part1
244461 | Deployment Backout Plan - Documentation (Placeholder)
1158 -Proj
244159 | Accessibility - SM Key board focus
244158 | Accessibility - GED HSED Search filter modal focus
243485 | ANALYSIS_ Accessibility Manual Testing coverage
243495 | Asana Updates and Project clean up
243494 | Asana Updates and Project clean up

## Road Map
Projects for FY26 | Funding Source | Status | Notes | Dec | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May | June
REF ID 863_ Move CRM Newsletters to govDelivery.docx | WISEdata | Completed
REF ID 202511042 - CRM Team Accessibility Compliance | WISEdata | Completed
REF ID 862_ Role-Based Contact Communications via GovDelivery.docx | WISEdata | In progress
Tecnology Update- .Net Upgrade | WISEdata | To Do - FY2027
REF ID: 840 - CST Team Member App Development + Customer Survey | WISEdata | To Do - FY2027
LEAD - ELO Verify (Annual Effort) and Lead Annual work |  | To Do - FY2027
REF ID 2512182 - CRM work for 2026 Accountability Inquiry Period |  | To Do - FY2027
Pipelines for Dataverse Solutions (CST and LEAD) |  | To Do - FY2027
REF ID 875- RECAPCHA for School Directory |  | To Do - FY2027
Misc - Production Support
REF ID 2511251 - Automate School Modification Template Emails |  | To Do - FY2027 | Gabby to answer some Questions from Development Team. In order to come up with estimates

## Key
Category | Time Commitment | Examples | Time Characteristics
Bug Fix / Tech Debt | Short-Term (days/weeks/ 1 sprint) | Fixing critical login bug | Quick turnaround (< 1 week)
|  | Minor UI glitches | Immediate or scheduled fix
Enhancement / Tech Debt | Medium-Term (weeks/months/ 2 sprints to 4 sprints) | Adding a new search filter | Takes 2-8 weeks (1 sprint or more)
|  | Improving report generation | Requires planning and testing
Project | Long-Term (3 months and above/ 5 sprints and above) | Developing a new product | Duration of 3+ months
|  | Migrating to new architecture | Large scope with detailed phases
Initiative | Long-Term (Multiple years) | Multiple projects aligning with business startegies or Grant expectations | Duration of 1 year +
|  | Digital transformations or Enterprise application modernization or Cyber Security changes or creating application (s) due to new program area | Large scope with multiple projects and phases